**Project Scope**

**Objective:** interview, select and bring 2-3 veterans for 3 weeks period during Summer of 2019 for the purposes of cultural exchange and rehabilitation. Preparation must be complete in 6 weeks with a budget of $10k.

Such a project will provide much needed support for mentally or physically disabled soldiers who are not able to obtain such help in home country. The project is assumed to substantially help depressed or otherwise ill people and improve their recovery process.

Current total amount authorized for this project is $10k, however it might increase later as donations come in. Projected cost per soldier is $3000 with $1000 overhead budget. Date of completion or projected deliverable date is 07/01/2019.

**Project Scope:** For this Project team of 4 volunteers will get together and spit task equally based on personal education, profession and skills. Volunteers must commit to working at least 8 hours per week during 2-month period to accomplish project objective. At the initial stage US team is to reach out to local Ukrainian non-profit and obtain applications from the veterans. Criterias by which applications will be reviewed are the following:

* Severity of the condition
* Mobility of the applicant.
* Availability of treatment for particular illness in the home country.
* Personal statement
* Background check.
* HIPPA release with emphasis on current addiction problems.

Applicants must meet all the requirements and laws of international travel such as present of passport or travel documents.

Volunteers are to accomplish the following task: select the applicants, conduct all the necessary reviews and preparation for timely Visa application, subcontract the travel agency who will prepare for one on one interview with emigration officer, generate and prepare letters of support from WA senator or government officials, keep track of accounting and budgeting, booking and travel arrangements, lodging , meal supplies, local tours and event, develop psychological program with local doctors, assign a trainer or a coach for physical activities, ensure safe and healthy environment for applicants, conduct and ongoing track of improvement with doctors feedback, supply caregivers, ensure timely release of funds and obtain all necessary approvals for funding.   
Project will be considered successfully accomplished upon applicant’s arrival and leaving of US.   
Selection of applicants was conducted in timely and prompt matter providing equal opportunity for all applicants. Reviews of supplied documents was evaluated and recorded on file. Emigration professionals were hired and conducted mock interviews with selected applicants, background checks were conducted according to international and local laws and regulations. Supporting documents were obtained from WA government officials no later then by 3rd week since Project Start Date. All the accounting, funding and budgeting is up to date and recorded on file. Funds are released in time. Travel accommodation are booked, and confirmation numbers are recorded on file. Entertainment as well as medical care programs are established and approved by medical staff. Caregivers are scheduled and budgeted for. Doctor’s feedback and program progress is recorded and periodically evaluated. Safe return is ensured, and applicants are arrived back to the home country.