## Sheet1
Estimated Activity Cost
Activity | Name | Work days | Labor Rate | Labor Cost | Material Cost | Travel Cost | Total Cost
Selecting Volunteers | Anna | 4 | 0 | 0 | 0 | 0 | 0
Selection of Applicants | Olga, Ramona, Chirag, Anna | 11.5 | 0 | 0 | 0 | 0 | 0
Background check | Anna | 9 |  | 40 | 0 | 50 | 90$
Visa Preparation | Olena | 18.5 | 0 |  | 480 |  | 480
Travel Arangments | Chirag | 4 | 0 |  | 3600 |  | 3600
Medical Care | Anna, Chirag Ramona | 5 | 0 | 0 | 0 | 0 | 0
Return Home | Anna | 1 | 0 | 0 | 0 | 60 | 60

## Sheet2
Estimated Activity Cost
Activity | Name | Work days | Labor Rate | Labor Cost | Material Cost | Travel Cost | Total Cost
Selection of volunteers
Assigment of tasks
Breakdown of resposibilities
Confirm Budgets and funding
Selection of applicants
Send out program overview to UA
Collect Applications
Evaluate applicants
Make a selection
Send out confirmation of the selection
Backgound check
Collect police reports/med statmt.
Check for travel documents
Confirm med condition and mobility of applicants
Visa Preparation
Complete DS-160 for B1/B2 Visas
Senator's Letter of Support
Travel agency assigment
Mock Interviews
Shcedule Visa interview
Travel arangements
Book airfare
Lodging
Food
Medical Care
Assign Doctors and Caregivers
Develop and confirm medical program
Feedback and Program Evaluation
Geather Doctor's statements
Draft and summary of the program
Return Home
Flight back home.End of the program