## Sheet1
Risk | Impact | Likelihood of occurrence | Degree of Impact | Action on Trigger | Responsibility
Shortage of volunteers | Lower quality work done by less qualified people. Project completion extended due to wait for search for qualified volunteers. | Low | Medium | Reach out to other non-profits in WA. Seek more human power outside of available volunteers. | Anna
Budget Shortage | Might make parts of the Project impossible. | Low | High | immediately reach launch GoFundMe me campaign and try to raise needed amount. | Anna
Faked background check | Might select applicants with criminal history and behavioral problems | Low | Medium | Double check provided documents through trusted sources. | Ramona
Visa Denial | Project will be suspended | High | High | Review and reapply with more preparation. | Olga
Travel | Financial risk, if participants are not able to navigate through large airports and miss their plane. | Low | Medium | Contact the airline. Arrange new travel times. | Chirag
Return | Illegal emigration if participants reject to return to home county. | Low | Medium | Report such participants to Homeland Security Office. | Olena